## Feature List
MRI ERP Implementation Taxonomy — Feature List & QA Tracker
Existing functionality (from source) + items folded in from the DevOps board. DevOps Ref maps each feature to its story. See Comparison sheet for the full reconciliation.
# | Category | Feature | Description | Where it lives | Source | Dev Status | Tested? | QA Status | DevOps Ref | QA Notes
1 | Views & Navigation | Three top-level views | Switch between Business Process (default), System (MRI PMX), and Mapping (coverage matrix) views via the view switcher. | main.js · switchView() | Existing | Done | No | Not Tested | 3216
2 | Views & Navigation | View-specific hints | Contextual sub-heading explains what each view shows as you switch. | main.js · VIEW_HINTS | Existing | Done | No | Not Tested | 3278
3 | Views & Navigation | Module tab bar | Tab per MRI module in the System view; active tab is highlighted; clicking switches modules. | main.js · switchTab() / index.html | Existing | Done | Yes | Pass | 3218, 3228 | Tested and closed 15 Sept 2026.
4 | Views & Navigation | Value-stream tab bar | Tab per business value stream in the Business view, with supporting streams visually marked. | businessView.js · renderBusinessTabs() | Existing | Done | No | Not Tested | 3221
5 | Views & Navigation | Detail panel | Right-side slide-in panel opens on any process/sub click, showing full detail for that item. | panel.js / businessView.js | Existing | Done | No | Not Tested | 3217
6 | Views & Navigation | Expand / collapse sub-processes | Processes with sub-processes can be expanded individually or all at once (System view). | main.js · toggleExpandAll() | Existing | Done | No | Not Tested | 3219
7 | Views & Navigation | Keyboard shortcuts | Esc closes any modal/panel; Enter confirms add dialogs; Ctrl/Cmd+Enter saves the edit modal. | main.js · keydown handler | Existing | Done | No | Not Tested | 3279
8 | System (MRI PMX) View | Process/sub card grid | Columns of process and sub-process cards for the active MRI module. | grid.js | Existing | Done | Yes | Pass | 3218, 3228 | Tested and closed 15 Sept 2026.
9 | System (MRI PMX) View | MRI module reference | Panel shows the MRI navigation path (mri_title) for the process. | panel.js | Existing | Done | No | Not Tested | 3229
10 | System (MRI PMX) View | Setup prerequisites | Panel lists MRI configuration that must exist before the process can run (mri_prereqs). | panel.js | Existing | Done | No | Not Tested | 3229
11 | System (MRI PMX) View | Associated MRI screens | Panel lists supporting MRI screens with per-screen descriptions (mri_assoc). | panel.js | Existing | Done | No | Not Tested | 3229
12 | System (MRI PMX) View | Core activities & overview | Business description and the activities a person performs for each process. | panel.js | Existing | Done | No | Not Tested | 3217, 3229
13 | System (MRI PMX) View | 9 built-in MRI modules | CM, GL, AP, RM, Job Cost, Corporate AR, Budgeting & Forecasting, Investment Accounting, Fixed Asset Accounting. | data/index.js | Existing | Done | Yes | Pass | 3228 | Tested and closed 15 Sept 2026.
14 | Business Process View | CRE value-stream taxonomy | Business view organised as Level-1 value streams → Level-2 groups → Level-3 process cards. | business/index.js · valueStreams.js | Existing | Done | No | Not Tested | 3221
15 | Business Process View | Market variation detail | Per-item guidance that differs by market (UK, US, Pan-European), shown for the selected markets. | businessView.js · showBusinessPanel() | Existing | Done | No | Not Tested | 3223
16 | Business Process View | Vertical / sector detail | Colour-tagged per-sector guidance (Retail, Industrial, Office, Residential). | businessView.js | Existing | Done | No | Not Tested | 3224
17 | Business Process View | Standards & frameworks chips | Regulatory/standards tags on cards and in the panel signal compliance weight. | businessView.js | Existing | Done | No | Not Tested | 3225
18 | Business Process View | Market filter | Multi-select filter drives which market-variation blocks appear in the panel. | businessView.js · renderBusinessFilters() | Existing | Done | No | Not Tested | 3226
19 | Business Process View | Vertical filter | Multi-select filter hides cards not relevant to the chosen sectors. | businessView.js · matchesVerticals() | Existing | Done | No | Not Tested | 3227
20 | Business Process View | System-coverage filter | Filter cards by coverage tag (Full / Partial / Outside / Untagged). | businessView.js · matchesCoverage() | Existing | Done | No | Not Tested | 3241
21 | Business Process View | Enrichment flag | Cards seeded from the reference guide are flagged as needing Market/Vertical/Standards detail. | business/index.js · needsEnrichment (data flag); businessView.js renders it | Existing | Done | No | Not Tested | 3222
22 | Business Process View | Value-stream context | Panel shows the parent value stream, its note, and whether it is a supporting stream. | businessView.js | Existing | Done | No | Not Tested | 3221
23 | Mapping / Coverage View | Coverage matrix | Matrix of business domains (rows) × system modules (columns) with per-cell link counts. | mappingView.js · renderMapping() | Existing | Done | No | Not Tested | 3235
24 | Mapping / Coverage View | Gap highlighting | Domains with no system links are flagged as unmapped; coverage stats summarise the matrix. | mappingView.js / links.js | Existing | Done | No | Not Tested | 3237
25 | Mapping / Coverage View | Cell detail (visual flow) | Clicking a cell opens a business→system flow list of the linked process pairs. | mappingView.js · showCell() | Existing | Done | Yes | Pass | 3236 | Tested 2026-08-18
26 | Mapping / Coverage View | Coverage colour coding | Cells and chips colour-coded by coverage (Full / Partial / Outside; mixed shown distinctly). | mappingView.js · cellCoverage() | Existing | Done | No | Not Tested | 3235, 3239
27 | Mapping / Coverage View | Click-through navigation | From a cell flow, jump straight to the business or system item in its own view. | mappingView.js / main.js · navigateToLinked() | Existing | Done | Yes | Pass | 3232, 3236 | Tested 2026-08-18
28 | Edit Mode | Toggle edit mode | Enter/exit Edit Mode to reveal add/remove/edit controls across the grid. | main.js · toggleEdit() | Existing | Done | No | Not Tested | 3247, 3248
29 | Edit Mode | Add column / domain | Add a new column (System) or domain (Business). | addModal.js / businessView.js | Existing | Done | No | Not Tested | 3247, 3248
30 | Edit Mode | Add process / sub-process | Add processes and sub-processes inline; new items open for editing. | addModal.js / businessView.js | Existing | Done | No | Not Tested | 3247, 3248
31 | Edit Mode | Edit any item field | In-place modal edits title, description, activities, MRI fields, and client note. | editModal.js / businessEditModal.js | Existing | Done | No | Not Tested | 3247, 3248
32 | Edit Mode | Remove items | Delete columns, processes, and sub-processes (with undo). | main.js · removeItem() / businessRemove() | Existing | Done | No | Not Tested | 3247, 3248
33 | Edit Mode | Add custom module tab | Create a new custom module tab with its own name, icon, and header colour. | addModal.js · confirmAddTab() | Existing | Done | No | Not Tested | 3276
34 | Scope & Coverage Tagging | Scope tags (System) | Tag each item Core / Custom / Out-of-Scope by cycling; drives filtering and export. | main.js · cycleScope() | Existing | Done | No | Not Tested | 3243
35 | Scope & Coverage Tagging | Bulk-tag column scope | Set scope for every process/sub in a column at once. | main.js · bulkTagColumn() | Existing | Done | No | Not Tested | 3245
36 | Scope & Coverage Tagging | Scope filter (System) | Multi-select filter shows only selected scopes (Core/Custom/OOS/Untagged). | main.js · renderScopeFilter() | Existing | Done | No | Not Tested | 3246
37 | Scope & Coverage Tagging | Auto out-of-scope | Items not linked to any value stream can be treated as auto out-of-scope. | grid.js · effectiveScope() | Existing | Done | No | Not Tested | 3244
38 | Scope & Coverage Tagging | Coverage tags (Business) | Tag business processes Full / Partial / Outside for system coverage; bulk-tag per domain. | businessView.js · cycleCoverage()/bulkTagCoverage() | Existing | Done | No | Not Tested | 3238, 3242
39 | Scope & Coverage Tagging | Missing-link warning | Full/Partial items with no system link are flagged with a "link needed" warning. | businessView.js · coverageNeedsLink() | Existing | Done | No | Not Tested | 3240
40 | Cross-view Linkage | Business ⇄ system links | Each business process links to the MRI PMX process(es) that deliver it, with a coverage level. | links.js | Existing | Done | Yes | Pass | 3231, 3233 | Tested 2026-08-18
41 | Cross-view Linkage | Seed link template | Group-level seed mapping expands to per-process links at load; refined per client. | links.js · SEED_LINKS / GROUP_LINKS | Existing | Done | Yes | Pass | 3231 | Tested 2026-08-18
42 | Cross-view Linkage | Panel cross-references | Both panels show the linked items on the other side, navigable with one click. | main.js · renderLinkSection() | Existing | Done | Yes | Pass | 3231 | Tested 2026-08-18
43 | Cross-view Linkage | Inline link editor | Edit-mode mapping cards let you add/remove links and set coverage per process. | mappingView.js · buildDomainCard() | Existing | Done | No | Not Tested | 3233, 3234
44 | Cross-view Linkage | Add-link drill-down combobox | Searchable 3-step picker (Module → Process → Sub-process) to add a system link. | mappingView.js · openComboDropdown() | Existing | Done | No | Not Tested | 3233
45 | Versioning & Persistence | Save named versions | Save the full taxonomy state as a named, client-specific version. | versions.js / main.js · confirmSaveAs() | Existing | Done | Yes | Pass | 3250 | Tested and closed 15 Sept 2026.
46 | Versioning & Persistence | Load / rename / delete versions | Manage saved versions from the Versions side panel. | versionMenu.js / versions.js | Existing | Done | Yes | Pass | 3251 | Tested 2026-08-18
47 | Versioning & Persistence | Save changes to active version | Overwrite the active version in place while editing. | main.js · saveChangesToVersion() | Existing | Done | No | Not Tested | 3277
48 | Versioning & Persistence | localStorage persistence | Versions persist in the browser localStorage (per browser/machine). | versions.js | Existing | Done | Yes | Pass | 3250 | Tested and closed 15 Sept 2026.
49 | Versioning & Persistence | Full-state snapshots | A version captures data, custom modules, module visibility, links, and business data. | main.js / versions.js | Existing | Done | Yes | Pass | 3250 | Tested and closed 15 Sept 2026.
50 | Versioning & Persistence | Version badge + dirty indicator | Topbar badge shows the active version and an unsaved-changes dot. | main.js · updateVersionBadge() | Existing | Done | No | Not Tested | 3280
51 | Undo & Reset | Undo (up to 20 steps) | View-aware undo restores the correct module/view before each mutation. | state.js · snapshot() / main.js · undo() | Existing | Done | No | Not Tested | 3252
52 | Undo & Reset | Reset current tab | Restore the active module (System or Business) to its factory baseline. | main.js · resetTab() | Existing | Done | No | Not Tested | 3253
53 | Undo & Reset | Reset all | Restore every built-in module to original content. | main.js · resetAll() | Existing | Done | No | Not Tested | 3253
54 | Module Management | Per-module visibility | Show/hide module tabs; hidden modules are excluded from tabs and export. | main.js · toggleModuleVisible() | Existing | Done | No | Not Tested | 3254 | Board 3254 also mentions per-stream visibility, which is not separately implemented.
55 | Module Management | Visibility saved per version | Each client version remembers which modules are visible. | main.js / versions.js | Existing | Done | No | Not Tested | 3254
56 | Module Management | Auto-switch on hide | Hiding the active module moves to the first visible one. | main.js · applyModuleVisibility() | Existing | Done | No | Not Tested | 3254
57 | Document Export | Generate preview | Build an in-app document preview from the current view and options. | genModal.js · buildDoc() / buildBusinessPreview() | Existing | Done | No | Not Tested | 3255, 3256
58 | Document Export | Word export (.docx) | Download a branded Open Box .docx (System or Business content), generated with the docx library. | genModal.js · downloadWord() → docxExport.js · generateDocx(); house style from obDocStyle.js | Existing | Done | No | Not Tested | 3255
59 | Document Export | PDF export (print) | Open a print-ready styled page for Save-as-PDF. | genModal.js · downloadPDF(); house style from obDocStyle.js · houseStyleCSS() | Existing | Done | No | Not Tested | 3256
60 | Document Export | Content section toggles | Choose to include overview, activities, prerequisites, and associated screens. | genModal.js · buildDoc(); docxExport.js · processBlock() | Existing | Done | No | Not Tested | 3255
61 | Document Export | Scope include filters | Include/exclude Core, Custom, Out-of-Scope, and Untagged items in the document. | genModal.js · getScopeIncludes(); docxExport.js · scopePass() | Existing | Done | No | Not Tested | 3255
62 | Document Export | Scope summary table | Document opens with a table of process counts per scope (total vs included). | genModal.js · buildScopeSummary(); docxExport.js · generateDocx() | Existing | Done | No | Not Tested | 3255
63 | Document Export | Current-tab or all-modules scope | Export just the active module or all visible modules. | genModal.js · getDocTabs() / businessDocTabs() | Existing | Done | No | Not Tested | 3255
64 | Document Export | Business document mode | Business view exports overview/activities plus market variations, vertical detail, and standards. | docxExport.js · generateBusinessDocx(); genModal.js · buildBusinessPreview() | Existing | Done | No | Not Tested | 3255
65 | Detail Content | Client notes | Per-item free-text client note, editable in Edit Mode, shown in the panel and saved per version. | clientNote.js / businessEditModal.js | Existing | Done | Yes | Pass | 3249 | Tested and closed 15 Sept 2026.
66 | Detail Content | Scope / coverage badges | Panel badges show item type, MRI/Business origin, and scope/coverage status. | panel.js / businessView.js | Existing | Done | No | Not Tested | 3217, 3229
67 | Views & Navigation | Scroll a long tab bar | Tab bar scrolls horizontally when tabs exceed the viewport width so every module/stream stays reachable. | main.css · .tab-bar (overflow-x) | DevOps Backlog | Done | Yes | Pass | 3220 | Implemented in CSS; was absent from the original feature list. ¦ Tested 2026-08-18
68 | System (MRI PMX) View | Placeholder modules flagged (awaiting SME review) | Visibly flag provisional modules (Job Cost, Corporate AR, Budgeting & Forecasting) as awaiting SME review so provisional content is not presented as final. | — not yet implemented | DevOps Backlog | Not Started | No | Not Tested | 3230 | GAP: data files carry SME-review code comments, but there is no in-app flag.
69 | Multi-ERP (future) | Select the target ERP | Choose which ERP the System view + link set maps against, so the same business processes can map to different ERPs. | — not implemented (future) | DevOps Backlog | Not Started | N/A | Not Tested | 3257 | MoSCoW: Won’t (future). Single ALL_DATA today.
70 | Versioning & Persistence | Share a client version between users (export/import) | Export a saved version to a portable file and import it on another machine/teammate to recreate it faithfully. | — not implemented (future) | DevOps Backlog | Not Started | N/A | Not Tested | 3258 | MoSCoW: Won’t (future). CLAUDE.md confirms not built.
71 | Business Process View | Value-stream naming conventions with descriptions | Ensure each value stream has a clear, standardised naming convention accompanied by a description that explains its scope and purpose. | business/valueStreams.js · VALUE_STREAMS (label + note per stream; title + note per L2 group) | New Requirement | Done | Yes | Pass | 3270 | Story 3270 under Feature 3197 (CRE Powered Value Streams Taxonomy). Tested 2026-08-18. Confirmed Done 2026-09-14 — every value stream carries a label and a note, every L2 group a title and a note.
72 | Business Process View | Cross-market value-stream validation (US / UK) | Confirm that value-stream names and structures are meaningful for both US and UK markets — e.g. "Recoveries" (UK) vs "Service Charges" (US) — and reconcile terminology where they diverge. | — not yet implemented | New Requirement | Not Started | N/A | Not Tested | 3271 | Story 3271 under Feature 3197 (CRE Powered Value Streams Taxonomy). Board New as at 2026-09-15.
73 | Scope & Coverage Tagging | Tagging methodology review and taxonomy alignment | Review current scope and coverage tagging to confirm the most appropriate approach, including whether tags should align with the existing taxonomy structure or follow a separate scheme. | — not yet implemented | New Requirement | Not Started | N/A | Not Tested | 3272 | Story 3272 under Feature 3205 (Item-Level System Coverage Tag). Board New as at 2026-09-15.
74 | Security & Access Control | Security features and responsibility boundaries | Define who can change or edit the master copy, whether access should grant editing rights, and the responsibility boundaries between roles (e.g. consultant vs client vs admin). | — not yet implemented | New Requirement | Not Started | N/A | Not Tested | 3273 | Story 3273 under Feature 3269 (Security & Access Control). Board New as at 2026-09-15.
75 | Versioning & Persistence | Database persistence (replace localStorage) | Move version and taxonomy data from browser localStorage to a database backend so that data persists across browsers, machines, and users. | — not yet implemented | New Requirement | Not Started | N/A | Not Tested | 3274 | Story 3274 under Feature 3211 (Client Versions). Board New as at 2026-09-15.
76 | Versioning & Persistence | Version comparison (side-by-side diff) | Side-by-side diff between two saved versions to see what changed from the baseline when tailoring for a client. | — not yet implemented | Nice to Have | Not Started | N/A | Ready for Testing | 3281 | Future enhancement. Story 3281 under Feature 3211 (Client Versions). ¦ Development complete, ready for testing.
77 | Views & Navigation | Guided discovery workflow | Checklist or wizard walking a consultant through module selection, scope tagging, coverage mapping, and export. | — not in the codebase yet (board: Active, 13 pts) | Nice to Have | In Progress | N/A | Not Tested | 3282 | Story 3282 under Feature 3195 (View Switcher & Shared Shell). Board state Active (13 pts) as at 2026-09-15 — work started; nothing in the codebase yet.
78 | Versioning & Persistence | Duplicate a version | Clone an existing client version as a starting point for a similar client. | versionMenu.js · startDuplicate(); versions.js · duplicateVersion() | Nice to Have | Done | Yes | Pass | 3283 | Story 3283 under Feature 3211 (Client Versions). Tested 2026-08-18. Confirmed Done 2026-09-14 — Duplicate control on each card in the Versions panel.
79 | Document Export | Richer export templates | Branded documents with cover page, table of contents, and executive summary. Cover page and TOC delivered; executive summary outstanding. | docxExport.js · buildBrandedDocument() (cover + TOC) — executive summary not built | Nice to Have | In Progress | No | Not Tested | 3284 | Partially delivered: cover page and auto table of contents built by the Open Box house-style export (70a941a, fa6d8fb); cover client name added 2026-09-14 (d349d98). Executive summary is the only outstanding element. Story 3284 under Feature 3213 (Word & PDF Export).
80 | Mapping / Coverage View | Progress dashboard | In-app view showing discovery completion (% scoped, % mapped, % enriched) per module. | — not yet implemented | Nice to Have | Not Started | N/A | Not Tested | 3285 | Future enhancement. Story 3285 under Feature 3204 (Coverage Mapping Matrix).
81 | Edit Mode | Attach evidence to processes | Link screenshots, documents, or meeting notes to individual processes as supporting artefacts. | — not yet implemented | Nice to Have | Not Started | N/A | Not Tested | 3286 | Future enhancement. Story 3286 under Feature 3210 (Edit Mode Content Authoring).
82 | Versioning & Persistence | Search / filter versions | Allow users to search or filter the versions list by name so they can quickly locate a saved client version when the list is long. | — not yet implemented | Nice to Have | Not Started | N/A | Not Tested | 3287 | Added 2026-08-18. Future enhancement — search/filter versions panel when version count grows.
83 | Versioning & Persistence | Discovery Baseline built-in version | Default landing version for a new engagement: loads the full taxonomy and link set with every scope and coverage tag cleared, so discovery starts untagged. Read-only. | main.js · loadVersion() / clearAllTags(); state.js · suppressAutoScope; versionMenu.js | Existing | Done | No | Not Tested | — Feature "Discovery Baseline template" (no story id in export) | App-only when identified 2026-09-09; the 2026-09-14 board export raised a matching Feature ("Discovery Baseline template"). Still has no user story beneath it.
84 | Versioning & Persistence | Built-in version edit lock | Save Changes is hidden and overwrite is blocked while a built-in baseline (Original / Discovery Baseline) is active, so factory content cannot be overwritten. | state.js · BUILTIN_VERSIONS; main.js · updateSaveChangesBtn() / saveChangesToVersion() | Existing | Done | No | Not Tested | — none (story needed) | App-only feature with no DevOps story — one should be raised. Identified 2026-09-09.
85 | Document Export | Client name on cover from version title | The document cover and footer take the client name from the saved version title; the built-in baselines fall back to a "Client Name" placeholder. | genModal.js · coverClientName(); docxExport.js · buildBrandedDocument() | Existing | Done | Yes | Pass | — none (story needed) | Added 2026-09-14 (commit d349d98). Verified by unzipping the generated .docx — the cover runs and footer1.xml both carry the version title. No DevOps story yet.
86 | Versioning & Persistence | Original factory content baseline version | Restores every built-in module to factory content with its original scope and coverage tags and the full seeded link set — the fully-linked reference template, as distinct from the untagged Discovery Baseline. | main.js · loadVersion('original'); data/index.js · ORIGINAL_DATA; links.js · seedLinks() | DevOps Backlog | Done | No | Not Tested | — Feature "Fully linked Original Factory Content template" (no story id in export) | Added from the 2026-09-14 board export, which raised this as a Feature. Built but had no tracker row and still has no user story beneath the feature.
87 | Scope & Coverage Tagging | Proposed Scope Tagging | Lets Open Box record, on either side of the taxonomy, where discovery has identified potential value add beyond what the client does today — a flag orthogonal to the existing coverage/scope tags, so the current-state tag is preserved. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3350 | Added 2026-10-01. DevOps Feature 3350. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
88 | Scope & Coverage Tagging | Flag a value-stream process as Proposed Scope | A Propose control on each Value Streams card in Edit Mode; flagging it does not change the coverage tag; the card shows both tags together; saved with the version. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3352 | Added 2026-10-01. DevOps User Story 3352. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
89 | Scope & Coverage Tagging | Flag an MRI PMX system process as Proposed Scope | A Propose control on each System view card in Edit Mode; the existing scope tag (Core/Custom/Out of scope) is retained; saved with the version. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3353 | Added 2026-10-01. DevOps User Story 3353. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
90 | Scope & Coverage Tagging | Capture the value-add rationale for a proposal | Both edit modals expose a Proposed Scope checkbox and rationale field; the rationale appears in the detail panel and generated document; unticking clears it. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3354 | Added 2026-10-01. DevOps User Story 3354. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
91 | Scope & Coverage Tagging | Distinguish a proposal from agreed client scope at a glance | Proposals use a distinct marker and dashed treatment, differing by shape as well as colour for colour-blind legibility; the panel states the item is a recommendation, not agreed scope. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3355 | Added 2026-10-01. DevOps User Story 3355. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
92 | Scope & Coverage Tagging | Style the Proposed Scope tag to the Open Box brand palette | The ✦ PROPOSED chip and related badges use the Open Box brand colour (CSS var(--prop) / var(--prop-accent)). | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3356 | Added 2026-10-01. DevOps User Story 3356. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
93 | Scope & Coverage Tagging | Bulk-propose or clear proposals for a column | The Tag all menu in both views offers Propose all / Clear proposals, applied to every process and sub-process in the column, leaving coverage/scope tags untouched; one undo step. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3351 | Added 2026-10-01. DevOps User Story 3351. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
94 | Scope & Coverage Tagging | Filter both views by Proposed Scope | A Proposed Scope toggle in both view filter bars narrows the existing coverage/scope selection rather than replacing it. Verified: toggling it hides non-proposed items and shows "No items match the selected filters" on empty columns. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3357 | Added 2026-10-01. DevOps User Story 3357. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
95 | Versioning & Persistence | Clear proposals when loading the Discovery Baseline | Loading the Discovery Baseline clears item proposals and proposed links on both sides, leaving the agreed link set intact (main.js clearProp / link filter on load). | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3358 | Added 2026-10-01. DevOps User Story 3358. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
96 | Cross-view Linkage | Proposed Scope Propagation Across Links | Carries a proposal across existing business↔system links so it is only captured once; derivation is deliberately one-hop only to avoid cascading through the link graph. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3359 | Added 2026-10-01. DevOps Feature 3359. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
97 | Cross-view Linkage | Imply a proposal across links in both directions | Flagging either side of a linked pair marks its linked counterparts as implied (derived); implied items render hollow/distinct from direct proposals, per links.js refreshDerivedProposals. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3360 | Added 2026-10-01. DevOps User Story 3360. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
98 | Cross-view Linkage | Prevent proposal propagation from cascading | Derivation reads only the directly-set `proposed` flag, never an implied one, so implication stops after one hop — confirmed in links.js comments and logic. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3361 | Added 2026-10-01. DevOps User Story 3361. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
99 | Cross-view Linkage | Propose a link that does not exist today | addLink() takes a `proposed` flag and toggleLinkProposed() exists; proposed links render dashed/distinct (map-chip-proposed, cell-flow-chip-proposed CSS). | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3362 | Added 2026-10-01. DevOps User Story 3362. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
100 | Cross-view Linkage | Keep proposed links out of agreed-scope derivation | linkedSystemIds()/hasLink() filter out `proposed` links before deriving agreed scope (links.js), so a proposed link cannot lift an item out of auto out-of-scope. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3363 | Added 2026-10-01. DevOps User Story 3363. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
101 | Document Export | Value-Add Proposals Document | Turns captured proposals into a client-facing section, excluded from generated documents unless explicitly included. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3364 | Added 2026-10-01. DevOps Feature 3364. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
102 | Document Export | Exclude proposals from generated documents by default | The export options include a Proposed Scope checkbox defaulting to unticked (genModal.js / docxExport.js inclProposed = false); no proposal content appears unless it is ticked. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3365 | Added 2026-10-01. DevOps User Story 3365. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
103 | Document Export | Generate a Value-Add Proposals section | With Proposed Scope ticked, the document gains a Value-Add Proposals section grouped by side/module, opening with a recommendations-not-agreed-scope disclaimer (docxExport.js proposalsBlocks()). | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3366 | Added 2026-10-01. DevOps User Story 3366. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.
104 | Document Export | Nest linked counterparts under each proposal | Each proposal entry lists its linked counterparts as supporting detail, with proposed links marked as such in the list. | src/components/proposalField.js, grid.js, businessView.js, genModal.js, docxExport.js; src/data/links.js | DevOps Backlog | Done | No | Ready for Testing | 3367 | Added 2026-10-01. DevOps User Story 3367. Implementation confirmed present by code inspection; core flow (propose a card, filter by Proposed Scope) smoke-tested in browser — no formal QA test pass run yet.

## Comparison
DevOps Backlog ⇄ App Feature Comparison
Board export 2026-09-15: 60 user stories, 224 story points — 8 Pending Feedback, 22 Resolved, 1 Active, 1 Development, 9 Closed, 1 Testing, 4 Analysis, 14 New. 46 of 60 progressed beyond New; 99 of 224 pts Resolved/Closed. 2 stories still read "New" although the tracker records them built. 4 app features have no story (Feature List #83-#86).
A · Matched — board story ↔ existing feature
DevOps ID | Story title | MoSCoW | Board state | Pts | Matched feature(s) | Actual (in code) | Notes / discrepancy
3216 | Switch between the three engagement views | Must | Pending Feedback | 3 | Three top-level views | Done (in code)
3217 | Open a detail panel for any card | Must | Resolved | 2 | Detail panel; Core activities & overview | Done (in code)
3218 | Browse the Tab-Column-Card hierarchy | Must | Pending Feedback | 2 | Process/sub card grid; Module tab bar | Done (in code)
3219 | Expand and collapse sub-processes | Should | Development | 3 | Expand / collapse sub-processes | Done (in code)
3221 | Browse CRE value streams | Must | Resolved | 3 | CRE value-stream taxonomy; Value-stream tab bar | Done (in code)
3222 | See which cards still need enrichment | Should | Analysis | 2 | Enrichment flag | Done (in code)
3223 | View market variation for a process | Should | Analysis | 3 | Market variation detail | Done (in code)
3224 | View vertical/sector detail for a process | Should | Pending Feedback | 3 | Vertical / sector detail | Done (in code)
3225 | See standards and frameworks on a process | Could | Pending Feedback | 2 | Standards & frameworks chips | Done (in code)
3226 | Filter value streams by market | Should | Pending Feedback | 2 | Market filter | Done (in code)
3227 | Filter value streams by vertical | Should | Pending Feedback | 2 | Vertical filter | Done (in code)
3228 | Browse the MRI PMX system taxonomy | Must | Resolved | 3 | Process/sub card grid; 9 built-in MRI modules | Done (in code)
3229 | See MRI setup detail for a system process | Must | Resolved | 3 | MRI module reference; Setup prerequisites; Associated screens | Done (in code)
3231 | See linked counterparts in both directions | Must | Closed | 3 | Panel cross-references | Done (in code) | Board Closed as at 2026-09-15; implemented in code.
3232 | Navigate to a linked counterpart | Must | Closed | 3 | Click-through navigation | Done (in code) | Board Closed as at 2026-09-15; implemented in code.
3233 | Add a link in Edit Mode | Must | Closed | 5 | Inline link editor; Add-link drill-down combobox | Done (in code) | Board Closed as at 2026-09-15; implemented in code.
3234 | Remove a link in Edit Mode | Must | Closed | 3 | Inline link editor (remove) | Done (in code) | Board Closed as at 2026-09-15; implemented in code.
3235 | View the coverage mapping matrix | Should | Resolved | 5 | Coverage matrix; Coverage colour coding | Done (in code)
3236 | Drill into a matrix cell | Should | Closed | 3 | Cell detail (visual flow) | Done (in code)
3237 | Identify coverage gaps | Should | Resolved | 3 | Gap highlighting | Done (in code)
3238 | Tag a value-stream process with system coverage | Must | Resolved | 3 | Coverage tags (Business) | Done (in code)
3239 | See context for a coverage tag on hover | Should | New | 2 | Coverage colour coding (coverageTooltip) | Done (in code) | Tooltip exists in code (coverageTooltip); feature #26 Done. Board still New as at 2026-09-15 — needs moving.
3240 | Be warned when a covered process is unlinked | Must | Resolved | 3 | Missing-link warning | Done (in code)
3241 | Filter value streams by system coverage | Should | Resolved | 3 | System-coverage filter | Done (in code)
3242 | Bulk-tag a column's coverage | Could | Resolved | 3 | Coverage tags (Business) — bulk per domain | Done (in code)
3243 | Tag a system process's scope | Should | Pending Feedback | 3 | Scope tags (System) | Done (in code)
3244 | Auto-derive out-of-scope for unlinked processes | Should | New | 5 | Auto out-of-scope | Done (in code) | Feature #37 Done (grid.js · effectiveScope). Board still New as at 2026-09-15 — needs moving.
3245 | Bulk-tag a system column's scope | Could | Resolved | 3 | Bulk-tag column scope | Done (in code)
3246 | Filter the system view by scope | Should | Resolved | 3 | Scope filter (System) | Done (in code)
3247 | Add, edit and remove business items | Must | Resolved | 5 | Add / Edit / Remove items (business) | Done (in code)
3248 | Add, edit and remove system items | Must | Analysis | 5 | Add / Edit / Remove items (system) | Done (in code)
3249 | Capture a client note on an item | Should | Resolved | 3 | Client notes | Done (in code)
3250 | Save a named client version | Must | Resolved | 5 | Save named versions; Full-state snapshots | Done (in code)
3251 | Load, rename and delete versions | Must | Closed | 3 | Load / rename / delete versions | Done (in code)
3252 | Undo recent changes | Should | Resolved | 3 | Undo (up to 20 steps) | Done (in code)
3253 | Reset to original content | Could | Resolved | 2 | Reset current tab; Reset all | Done (in code)
3254 | Toggle module and stream visibility | Could | Resolved | 3 | Per-module visibility; Visibility saved per version | Partially built | PARTIAL: module visibility built (#54-#56); per-stream (value-stream) visibility never implemented. Board Resolved as at 2026-09-15 — query whether the story was closed on partial delivery.
3255 | Export to Word | Should | Resolved | 5 | Word export; Scope summary; Business document mode | Done (in code)
3256 | Export to PDF | Should | Resolved | 3 | PDF export (print) | Done (in code)
B · On board only — not in the app baseline (add / assess)
DevOps ID | Story title | MoSCoW | Board state | Pts | Actual (in code) | Action / note
3220 | Scroll a long tab bar | Could | Closed | 2 | Done (in code) | Implemented via CSS overflow; added to Feature List. Board Closed as at 2026-09-15 — reconciled.
3230 | See placeholder modules flagged | Could | New | 2 | Not built | GAP — no in-app flag on placeholder modules; only SME-review code comments. Added to Feature List as Not Started.
3257 | Select the target ERP | Won't | New | 8 | Not built | Future / multi-ERP. Single ALL_DATA today. Added to Feature List as Not Started.
3258 | Share a client version between users | Won't | New | 5 | Not built | Future export/import. Confirmed absent (CLAUDE.md). Added to Feature List as Not Started.
C · Previously app-only — now have DevOps stories
Feature | Category | Where it lives | Note
View-specific hints | Views & Navigation | main.js · VIEW_HINTS | Story 3278 created. Board Pending Feedback as at 2026-09-15.
Keyboard shortcuts | Views & Navigation | main.js · keydown handler | Story 3279 created. Board Testing as at 2026-09-15.
Add custom module tab | Edit Mode | addModal.js · confirmAddTab() | Story 3276 created. Board Analysis as at 2026-09-15.
Save changes to active version | Versioning & Persistence | main.js · saveChangesToVersion() | Story 3277 created. Board Resolved as at 2026-09-15.
Version badge + dirty indicator | Versioning & Persistence | main.js · updateVersionBadge() | Story 3280 created. Board Resolved as at 2026-09-15.
D · New requirements — added to DevOps board
Feature | Category | Description | Suggested story title | Dev Status | Action
Value-stream naming conventions with descriptions | Business Process View | Ensure each value stream has a clear, standardised naming convention with a description of its scope and purpose. | Standardise value-stream names and descriptions | Closed | Added: Story 3270
Cross-market value-stream validation (US / UK) | Business Process View | Confirm that value-stream names are meaningful for both US and UK markets (e.g. "Recoveries" vs "Service Charges") and reconcile terminology. | Validate value-stream naming across US/UK markets | New | Added: Story 3271
Tagging methodology review and taxonomy alignment | Scope & Coverage Tagging | Review scope/coverage tagging approach and confirm whether tags should align with the existing taxonomy structure. | Review and align tagging methodology | New | Added: Story 3272
Security features and responsibility boundaries | Security & Access Control | Define who can edit the master copy, whether access grants editing rights, and responsibility boundaries between roles. | Define security model and access control | New | Added: Story 3273
Database persistence (replace localStorage) | Versioning & Persistence | Move data from browser localStorage to a database so it persists across browsers, machines, and users. | Add database backend for persistence | New | Added: Story 3274
E · Nice to have — on the board, not in the delivered baseline
DevOps ID | Story title | MoSCoW | Board state | Pts | Actual (in code) | Action / note
3281 | Version comparison (side-by-side diff) | Could | New | 8 | Not built | Future enhancement. Feature List #76.
3282 | Guided discovery workflow | Could | Active | 13 | Not built | Future enhancement. Feature List #77.
3283 | Duplicate a version | Could | Closed | 3 | Done (in code) | Built: versionMenu.js · startDuplicate(). Feature List #78.
3284 | Richer export templates | Could | New | 8 | Partially built | Cover page + TOC built; executive summary outstanding. Feature List #79.
3285 | Progress dashboard | Could | New | 8 | Not built | Future enhancement. Feature List #80.
3286 | Attach evidence to processes | Could | New | 8 | Not built | Future enhancement. Feature List #81.
3287 | Search / filter versions | Could | New | — | Not built | Future enhancement. Feature List #82.

## Summary
Feature & QA Summary
Development Status
Dev Status | Count | % of total
Done
In Progress
Not Started
Backlog
Blocked
Total
QA Status
QA Status | Count | % of total
Not Tested
In Progress
Pass
Failed
Blocked
Total
Source
Source | Count | % of total
Existing
DevOps Backlog
New Requirement
Nice to Have
Total
Backlog Comparison
Board stories total | 60
Matched to a tracker feature | 60
On board only (section B) | 4
In app only (no story) | 4
New requirements still to raise | 0
Board "New" but built in code | 2

## Status Key
Status Key — allowed values
Column | Allowed values & meaning
Source | Existing = already in the app (source-derived baseline). DevOps Backlog = folded in from the board. New Requirement = raised during review. Nice to Have = future enhancement.
Dev Status | Done = built in the codebase. In Progress = under active development (board Active/Development, or partially built). Not Started / Backlog = planned only. Blocked = cannot proceed.
Tested? | Yes = QA complete. No = not yet tested. Partial = some testing done. N/A = no QA needed.
QA Status | Not Tested · In Progress · Pass · Failed · Blocked — the outcome/progress of QA.
DevOps Ref | Matched Azure DevOps story ID(s). Multiple IDs = feature spans several stories.
QA Notes | Free text — discrepancies, defects, evidence links, tester, or context.
Comparison sheet | A = matched (board story ↔ feature); B = on board only; C = previously app-only, now has a story; D = new requirements added to the board; E = nice-to-have stories. "Actual (in code)" = what the source actually does, vs the board state. "Board state" and "Pts" come from the latest DevOps export (2026-09-15).